# Appendix C.3 — Price Proposal (Narrative)

Proposal title: A Closed-Loop, Mechanistically Grounded Research Engine for Complex Neuropsychiatric Disease: Schizophrenia to Bipolar Disorder Prime organization: Institute for Physical AI (IPAI), Purdue University SAM.gov UEI: Purdue University [to confirm before submission] Program: ARPA-H-SOL-26-155 (Intelligent Generator of Research, IGoR), Proactive Health Office Award instrument: Other Transaction Period of performance: 60 months (Phase I Months 0–18; Phase II Months 18–36; Phase III Months 36–60) Date: 2026-08-06

## Cover Table

| Field | Amount |
| --- | --- |
| Total price, all phases (inclusive of resource sharing) | ~$45,200,000 |
| Total ARPA-H request (all phases) | ~$42,900,000 |
| Total Performer in-kind resource sharing | ~$2,300,000 |
| Phase I subtotal (ARPA-H funded, Months 0–18) | ~$11,500,000 |
| Phase II subtotal (ARPA-H funded, Months 18–36) | ~$13,100,000 |
| Phase III subtotal (ARPA-H funded, Months 36–60) | ~$18,400,000 |
| Government percentage / amount | ~94.9% / ~$42,900,000 |
| Performer (in-kind) percentage / amount | ~5.1% / ~$2,300,000 |

Phase arithmetic: ~$11.5M + ~$13.1M + ~$18.4M = ~$42.9M (ARPA-H request). Government (~$42.9M) + Performer in-kind (~$2.3M) = ~$45.2M total project value. ✓

## Table of Contents

- Level of Effort and Labor

- Equipment Purchases

- Travel

- Other Direct Costs (ODCs)

- Resource Sharing

## Per-Organization, Per-Phase Price Table (from Cost Model Table 1-A)

| Performer | Role / TAs | Phase I ()¦PhaseII() | Phase III ()¦5−yrTotal() |  |  |
| --- | --- | --- | --- | --- | --- |
| Purdue/IPAI — computational (Prime) | PI (Grama); TA1/TA2 engine; Anne Carpenter (TA1 co-lead, computational morphology); PhD students; research engineers; disease-modeling postdoc; ~57% F&A | 1,800,000 | 2,000,000 | 2,700,000 | 6,500,000 |
| Purdue — Tegtmeyer lab (TA4-academic) | iPSC-neuron wet-lab; multimodal readouts incl. single-cell calcium imaging; Matt also TA1 disease-modeling contributor; Ph I equipment ~$1.4M front-loaded | 2,000,000 | 1,700,000 | 2,300,000 | 6,000,000 |
| Purdue total (prime) |  | 3,800,000 | 3,700,000 | 5,000,000 | 12,500,000 |
| Cytognosis Foundation (Sub) | TA1 model lead; TA1-TA2 hypothesis lead; Shahin + PM (Purcell) + SWE/Architect + ~5 ML/comp-bio; 15% de minimis F&A | 2,400,000 | 2,900,000 | 4,200,000 | 9,500,000 |
| SIFT (Sub) | TA2-TA3 + TA3 + TA3-TA4 (scoped VOI layer under Cytognosis+IPAI TA2 lead); Dan Bryce lead; Goldman advisor; 24,204 labor hours; 70% Bryce / 30% Goldman; DL $4,094,437; indirect $2,199,941; travel $69,747; fee $636,412 | 2,000,000 | 2,200,000 | 2,800,000 | 7,000,000 |
| Cellanome (Sub) | TA4-industry arm; R3200 RENT-and-we-run base; single-cell calcium imaging integration; confirm via quote | 1,400,000 | 1,800,000 | 2,800,000 | 6,000,000 |
| Shared program compute | GPU/cloud; TA1+TA2; program line not loaded on one org; partially shiftable to IPAI HPC in-kind | 600,000 | 800,000 | 1,100,000 | 2,500,000 |
| TA4 sequencing CRO | scRNA-seq + Perturb-seq; CRO subaward; Illumina optional in-kind only | 400,000 | 600,000 | 1,000,000 | 2,000,000 |
| McLean / HMS (Sub) | Clinical; W. Brad Ruzicka MD/PhD; cohort interpretation; data governance; no new clinical trials | 200,000 | 200,000 | 300,000 | 700,000 |
| Duane Valz — legal/IP (consultant) | OT review; IP/field-of-use; subaward/NDA; OSS licensing; billed through Cytognosis; ~$750/hr × ~150–300 hrs; [FLAG Duane + Purdue SPS for scope/rate confirmation] | 80,000 | 60,000 | 60,000 | 200,000 |
| Cross-team / integration / reserve | DDD workshop; bake-offs; connect-a-thon; ~6% reserve | 600,000 | 800,000 | 1,100,000 | 2,500,000 |
| TOTAL (ARPA-H request) |  | ~$11,480,000 | ~$13,060,000 | ~$18,360,000 | ~$42,900,000 |
| (display as) |  | ~$11.5M | ~$13.1M | ~$18.4M | ~$43M |

Phase arithmetic: $11.48M + $13.06M + $18.36M = $42.9M ✓

Note on in-kind attribution: Total project value including ~$2.3M Performer in-kind = ~$45.2M. The in-kind is attributable as: IPAI/Purdue HPC compute (Anvil/Brown, NSF ACCESS rates) ~$2.0M; Purdue wet-lab facilities ~$0.15M; Cellanome instrument/run credits ~$0.16M. In-kind items are SEPARATE from the ARPA-H ask above; total project value ~$45.2M. Illumina and Phylo are not budgeted performers: Illumina = optional in-kind sequencing/cloud only; Phylo = optional TA2 collaborator, not budgeted.

**[FLAG for Ananth + Shahin: confirm IGoR per-award ceiling so ~$43M headroom is confirmed. FLAG for Duane + Purdue SPS: commercial-sub salary-cap treatment (SIFT/Cellanome) — do not assume.]*

## Consolidated Basis of Estimate (BOE) Table (from Cost Model Table 6-A)

| ARPA-H Cost Category | Phase I ()¦PhaseII() | Phase III ()¦5−yrTotal() | % of Total |  |  |
| --- | --- | --- | --- | --- | --- |
| Direct Labor (fully burdened) | 4,700,000 | 6,600,000 | 7,500,000 | 18,800,000 | 43.8% |
| Materials | 600,000 | 800,000 | 1,000,000 | 2,400,000 | 5.6% |
| Equipment | 1,400,000 | 0 | 0 | 1,400,000 | 3.3% |
| Travel | 225,000 | 300,000 | 375,000 | 900,000 | 2.1% |
| Subcontracts & consultants | 550,000 | 700,000 | 950,000 | 2,200,000 | 5.1% |
| Other Direct Costs (ODC) | 1,725,000 | 2,075,000 | 3,100,000 | 6,900,000 | 16.1% |
| Indirect (F&A / Overhead) | 1,850,000 | 2,075,000 | 3,475,000 | 7,400,000 | 17.2% |
| Profit / Fee | 300,000 | 410,000 | 490,000 | 1,200,000 | 2.8% |
| Cross-team integration & reserve | 130,000 | 100,000 | 1,470,000 | 1,700,000 | 4.0% |
| TOTAL | ~$11,480,000 | ~$13,060,000 | ~$18,360,000 | $42,900,000 | 100% |

Reconciliation (three-way tie): - By-category sum: 18.8 + 2.4 + 1.4 + 0.9 + 2.2 + 6.9 + 7.4 + 1.2 + 1.7 = $42.9M ✓ - By-performer sum: 6.5 + 6.0 + 9.5 + 7.0 + 6.0 + 2.5 + 2.0 + 0.7 + 0.2 + 2.5 = $42.9M ✓ - By-phase sum: 11.48 + 13.06 + 18.36 = ~$42.9M ✓

These figures are mirrored in the Appendix C.4 workbook and finalized to the cent at OT negotiation.

## Section 1: Level of Effort and Labor

### Overview

PsychIGoR fields approximately 23 funded full-time equivalents (FTEs) per year across eight performing organizations. Total direct labor over 60 months is approximately $18.8M, representing 43.8% of the ARPA-H request, with approximately 130,000 funded labor hours at a blended fully-loaded rate of approximately $145/hour.

Answering ARPA-H’s stated concern about junior staffing: Appendix C.3 of the solicitation states that proposers are discouraged from staffing efforts with junior personnel to appear more cost-effective. PsychIGoR answers this directly. Every performing organization contributes substantive senior expertise: four PhD faculty (Grama, Carpenter, Tegtmeyer, Ruzicka) each contribute 2–3 person-months per year for scientific strategy, laboratory oversight, and translational framing. The computational and engineering execution is carried by senior postdoctoral researchers, research scientists, and software engineers (all at 1.0 FTE) individually named where confirmed and drawn from the top of the labor-market range for computational biology and ML engineering. SIFT contributes 24,204 labor hours of senior standards-engineering depth (70% Bryce / 30% Goldman and engineers). Cytognosis contributes approximately 5 ML/comp-bio FTE plus PM and Architect, including a Software and Systems Architect (a planned Cytognosis hire; Elham Jebalbarezi Sarbijan (IPAI) interim) at 1.0 FTE and a named PM (Patricia Purcell) at approximately 400 hours per year. PhD students at Purdue (two funded at 1.0 FTE each) are appropriate for their role: executing bench protocols under faculty supervision, not substituting for senior scientific decision-making.

### Labor Categories, Rates, and Person-Months by Organization

Purdue/IPAI — computational (Prime): ~5.75 FTE/year

| Person / Role | Appointment | PM/yr | FTE | Loaded $/yr |
| --- | --- | --- | --- | --- |
| Ananth Grama, PhD (PI, IPAI Director) | 12-mo academic | 3 | 0.25 | ~$57,000 (ARPA-H-funded at $228K cap × 0.25) |
| Anne Carpenter, PhD (TA1 co-lead; computational morphology/imaging-model lead; no bench; in-house IPAI/Purdue) | 12-mo (Purdue, ~Sep 2026) | 3 | 0.25 | ~$57,000 (ARPA-H-funded at $228K cap × 0.25; Purdue covers remainder of ~$300K base) |
| PhD student #1 (TA1 mechanistic modeling) | 12-mo student | 12 | 1.0 | ~$50,000 stipend + ~$35,000 tuition |
| PhD student #2 (TA1 / TA2 support) | 12-mo student | 12 | 1.0 | ~$50,000 stipend + ~$35,000 tuition |
| Research engineer (TA1/TA2 systems, Purdue) | 12-mo staff | 12 | 1.0 | ~$110,000 |
| Disease-modeling postdoc (TA1) | 12-mo staff | 12 | 1.0 | ~$80,000 |
| Senior postdoc / research scientist (computational morphology) | 12-mo staff | 12 | 1.0 | ~$85,000 |
| Purdue/IPAI Computational Subtotal |  |  | ~5.75 FTE | ~$510,000/yr |

Purdue — Tegtmeyer lab (TA4-academic): ~3.75 FTE/year

| Person / Role | Appointment | PM/yr | FTE | Loaded $/yr |
| --- | --- | --- | --- | --- |
| Matthew Tegtmeyer, PhD (TA4-academic experimental lead; also TA1 disease-modeling contributor) | 9-mo + 3 summer | 3 | 0.25 | ~$55,000 (25% of ~$220K base, below cap) |
| Postdoc (TA4 iPSC-neuron wet-lab) | 12-mo staff | 12 | 1.0 | ~$80,000 |
| Lab technician (wet-lab support, TA4) | 12-mo staff | 12 | 1.0 | ~$65,000 |
| Senior research scientist (TA4 assay methods) | 12-mo staff | 12 | 1.0 | ~$85,000 |
| Purdue Tegtmeyer lab Subtotal |  |  | ~3.75 FTE | ~$285,000/yr |

Cytognosis Foundation (Sub): ~5.5 FTE/year

| Person / Role | Appointment | PM/yr | FTE | Loaded $/yr |
| --- | --- | --- | --- | --- |
| Shahin Mohammadi, PhD (TA1/TA2 lead; CEO) | 12-mo, nonprofit | 6 | 0.5 | ~$140,000 (Rung-1 cap base $228K × 0.5 FTE base; + fringe + 15% de minimis OH; [rate pending comp finalization]) |
| Patricia Purcell (Project Manager, part-time/hourly) | Hourly | — | ~0.2 | ~$80,000 (~400 hrs/yr at ~$200/hr loaded) |
| Software and Systems Architect (planned Cytognosis hire; Elham Jebalbarezi Sarbijan (IPAI) interim) | 12-mo staff | 12 | 1.0 | ~$250,000 loaded |
| Senior ML/AI Engineer (TA2) | 12-mo staff | 12 | 1.0 | ~$260,000 loaded |
| ML Research Scientist (TA1/TA2) | 12-mo staff | 12 | 1.0 | ~$240,000 loaded |
| Computational Biologist #1 (TA1) | 12-mo staff | 12 | 1.0 | ~$210,000 loaded |
| Computational Biologist #2 (TA1) | 12-mo staff | 12 | 1.0 | ~$210,000 loaded |
| Cytognosis Personnel Subtotal |  |  | ~5.7 FTE | ~$1,390,000/yr |

Patricia Purcell (Project Manager): ISO (Appendix A §5.5) requires a named PM. Purcell serves part-time/hourly (~400 hrs/yr at ~$200/hr loaded = ~$80K/yr). Charged through Cytognosis. Total 5-year PM cost: ~$400,000. Will be reclassified to Direct Labor at submission with confirmed hourly rate.

SIFT (Sub): 24,204 labor hours over 5 years; Dan Bryce lead (70%), Robert Goldman advisor (30%)

| Category | Dan’s confirmed figure |
| --- | --- |
| Direct Labor (fully burdened) | $4,094,437 |
| Indirect Costs | $2,199,941 |
| Travel | $69,747 |
| Profit / Fee | $636,412 |
| Total | ~$7,000,537 (~$7.0M) |

SIFT builds on its XPlan experimental planner (DARPA SD2) for TA2-TA3 and leads TA3 (LabOP backbone). Note: SIFT operates as a scoped VOI layer under Cytognosis+IPAI TA2 co-lead; SIFT does not co-lead TA2. [SIFT draft, pending Dan’s revision.]

McLean / HMS (Sub): ~0.2 FTE/year, ~$70,000/year

| Person / Role | PM/yr | FTE | Loaded $/yr |
| --- | --- | --- | --- |
| W. Brad Ruzicka, MD/PhD (clinical co-lead) | 2–3 | 0.17–0.25 | ~$70,000 (loaded with HMS F&A); $228K × 0.20 FTE = ~$45,600 ARPA-H salary; HMS covers remainder of ~$250K base |

No new human subjects research. Uses existing cohort data under originating IRB and NIH GDS policy. 5-year total: ~$0.7M.

Duane Valz (legal/IP consultant; not key personnel): Outside counsel for IP strategy, OT/Other-Transaction agreement review, data-use and IP-flow governance, field-of-use splits; billed through Cytognosis. Rate ~$750/hr × ~150–300 hrs total = $200,000 over 5 years. [FLAG Duane for scope/rate confirmation; FLAG Ananth for financial verification.]

Cellanome (Sub): Personnel + R3200 instrument time embedded in sub total. Operating model (RENT-and-we-run base; R3200 in-lab vs. send-out opex) TBD pending BD quote. 5-year total: $6.0M. [FLAG: pending Cellanome BD + Psomagen quotes.]

Carpenter computational continuity within the IPAI/Purdue prime (no separate Broad sub-award)

Anne Carpenter’s TA1 co-lead scope (code, models, analysis continuity) is fully in-house at IPAI/Purdue. There is no standalone Broad sub-award. The JUMP Cell Painting open dataset (~$0.15M in-kind) is a public Broad open-data resource (Section 5), independent of Anne’s employment at Purdue.

### Program-Wide FTE Summary by Phase

| Organization | Phase I (18 mo) | Phase II (18 mo) | Phase III (24 mo) | Avg FTE/yr |
| --- | --- | --- | --- | --- |
| Purdue/IPAI Computational (Prime) | 5.75 | 5.75 | 6.5 | 6.0 |
| Purdue Tegtmeyer lab (TA4-academic) | 3.75 | 3.75 | 4.0 | 3.8 |
| Cytognosis (Sub) | 5.7 | 5.7 | 6.5 | 5.9 |
| SIFT (Sub) | 2.5–3.0 | 2.5–3.0 | 2.5 | 2.7 |
| McLean / HMS (Sub) | 0.2 | 0.2 | 0.25 | 0.2 |
| Cellanome (Sub) | 2.5 | 3.0 | 3.5 | 3.0 |
| Program Total | ~20.4 | ~21.0 | ~23.3 | ~21.6 FTE/yr |

### Salary Cap Statement

Executive Level II salary cap = $228,000, effective January 11, 2026 (NIH NOT-OD-26-034). This cap applies to the ARPA-H-funded portion of direct salary on this Other Transaction award, per the ARPA-H draft Model OT Agreement.

| Person | Org | Institutional base (est.) | Cap-bound? | ARPA-H-funded salary |
| --- | --- | --- | --- | --- |
| Ananth Grama, PhD (PI) | Purdue | ~$320,000 | Yes | $228,000 × 0.25 FTE = ~$57,000/yr; Purdue covers remainder |
| Anne Carpenter, PhD (TA1 co-lead; no bench; in-house IPAI/Purdue) | Purdue | ~$300,000 | Yes | $228,000 × 0.25 FTE = ~$57,000/yr; Purdue covers remainder |
| Matthew Tegtmeyer, PhD | Purdue | ~$220,000 | No | Full 0.25 FTE funded normally; verify if base rises above cap |
| W. Brad Ruzicka, MD/PhD | McLean/HMS | ~$250,000 | Yes | $228,000 × 0.20 FTE = ~$45,600/yr; HMS covers remainder |
| Shahin Mohammadi, PhD | Cytognosis | $228,000 (Rung 1 = cap exactly) | At cap | Charge $228K × 0.5 FTE = ~$114K/yr base; Rungs 2/3 above cap from unrestricted funds only, never from this award |
| Software Architect (planned Cytognosis hire; Elham Jebalbarezi Sarbijan (IPAI) interim) | Cytognosis | ~$200,000 est. | No | Below cap; 1.0 FTE funded normally |
| Senior ML/AI Engineer | Cytognosis | ~$190,000 est. | No | Below cap |
| Dan Bryce, PhD (SIFT) | SIFT | ~$200,000 est. | [FLAG Duane + Purdue SPS] | Commercial-sub salary-cap treatment; do not assume |
| PhD students × 2 (Purdue) | Purdue | ~$36,000–50,000 stipend | No | Well below cap |
| Cellanome / sequencing CRO staff | Commercial | ~$150,000–210,000 | [FLAG Duane + Purdue SPS] | Commercial-sub cap treatment; do not assume |

Grama, Carpenter, and Ruzicka have institutional bases modestly above the $228,000 cap, which is standard for senior faculty. This imposes no practical constraint because their ARPA-H-funded fractions are small (0.2–0.25 FTE). Shahin Mohammadi (Cytognosis CEO): compensation Rung 1 is pegged exactly to the HHS Executive Level II rate ($228,000), so the ARPA-H charge equals $228K × committed effort (0.5 FTE = ~$114K/yr base before fringe). Rungs 2 and 3 of his compensation ladder exceed the cap and are funded exclusively from unrestricted organizational funds, never from this award.

[FLAG Duane Valz + Purdue SPS: cap treatment on direct-salary component for commercial subs (SIFT, Cellanome). Do not assume they are uncapped or capped.]

### All Rates Are Fully Burdened

All rates in the tables above are fully burdened: base salary plus fringe benefits plus any directly applicable overhead where the organization applies it. Academic personnel follow 9-month and 12-month appointment conventions for person-month accounting. Rates are drawn from 2026 market data (BLS OEWS May 2024; NIH NRSA FY2026 for academic postdoc stipends).

## Section 2: Equipment Purchases (~$1.4M)

Total equipment over five years is approximately $1.4M, concentrated in Phase I at Purdue (Tegtmeyer lab stand-up for TA4 academic experimental arm). All items exceeding $10,000 will be accompanied by vendor quotes, past purchase orders, or equivalent backup documentation per Appendix C.3.

### Equipment Line Items

| Item | Organization | Phase | Qty | Unit price (est.) | Total (est.) | Backup docs required? |
| --- | --- | --- | --- | --- | --- | --- |
| High-content imaging system (Cell Painting / optical pooled screening; PerkinElmer Operetta CLS or BioTek Cytation equivalent) | Purdue (Tegtmeyer lab) | Phase I | 1 | ~$350,000 | ~$350,000 | Yes (>$10K); vendor quote |
| Spinning-disk confocal + calcium-imaging rig (Nikon Ti2 + spinning disk + perfusion chamber; single-cell Ca2+ imaging in iPSC-derived neurons) | Purdue (Tegtmeyer lab) | Phase I | 1 | ~$275,000 | ~$275,000 | Yes; vendor quote |
| Opentrons OT-2 liquid handler (LabOP-compatible; SiLA 2 interface) | Purdue and/or SIFT | Phase I | 2 | ~$30,000 | ~$60,000 | Yes; vendor quote |
| Lab fit-out (CO2 incubators, biosafety cabinets, centrifuges, plate readers) | Purdue (Tegtmeyer lab) | Phase I | lot | ~$150,000 | ~$150,000 | Yes; vendor quotes or past POs |
| iPSC-specific equipment (spinner flask bioreactor, additional plate reader) | Purdue (Tegtmeyer lab) | Phase I | lot | ~$120,000 | ~$120,000 | Yes; vendor quotes |
| Lab computing workstations + NAS | Purdue | Phase I | lot | ~$80,000 | ~$80,000 | Yes; vendor quotes |
| Software licenses (individual items generally <$10K) | Multiple | All | lot | — | ~$50,000 | No (items <$10K each) |
| Equipment reserve | Multiple | All | — | — | ~$115,000 | — |
| Phase I equipment subtotal |  |  |  |  | ~$1,400,000 |  |
| Phase II equipment subtotal |  |  |  |  | $0 | Equipment concentrated in Phase I |
| Phase III equipment subtotal |  |  |  |  | $0 |  |
| 5-year total |  |  |  |  | $1,400,000 |  |

### Rationale for Phase I Equipment Concentration

Tegtmeyer is establishing a new Purdue faculty wet-lab and is the academic experimental arm of TA4; the imaging and cell-biology equipment stand-up belongs to his bench. Carpenter is in-house at Purdue/IPAI in a purely computational capacity (no new wet-lab bench); no separate Broad sub-award. Deferring the imaging equipment to Phase II would delay Tegtmeyer’s experimental throughput and risk the Month 18 closed-loop milestone. Option A (full Phase I stand-up for Tegtmeyer’s lab) is adopted.

Note: any Purdue wet-lab construction or renovation is a capital cost covered by Purdue institutional funds; it is not a direct cost on this award.

## Section 3: Travel (~$0.9M)

Total travel over five years is approximately $0.9M. SIFT’s confirmed travel is $69,747 (per Dan’s cost breakdown). Each trip is justified against a specific TDD task or milestone.

### Travel Line Items

| Purpose | TDD task | Phase | Lead org / travelers | Destination | Travelers | Est. cost/traveler | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ARPA-H Domain-Driven Design (DDD) workshop (kickoff; all-team schema and interface co-design) | 1.5.0; 1.2.3; 1.3.3 | Phase I (Month 1–2) | IPAI/Purdue (host) | Washington DC or West Lafayette, IN | ~14 (all TA leads + ARPA-H PM) | ~$2,800 | ~$40,000 |
| TA3 bake-off #1 (cross-team protocol exchange; RFC-001 process) | 2.3.0; 2.3.1 | Phase II (Month 21–24) | SIFT (lead) | TBD (ARPA-H site) | ~8 | ~$2,000 | ~$16,000 |
| TA3 bake-off #2 (Phase II interoperability preparation) | 2.3.0; 2.3.2 | Phase II (Month 30–33) | SIFT (lead) | TBD | ~8 | ~$2,000 | ~$16,000 |
| TA3 bake-off #3 / connect-a-thon preparation | 3.3.3 | Phase III (Month 45–48) | SIFT (lead) | TBD | ~6 | ~$2,000 | ~$12,000 |
| SIFT travel (confirmed per Dan’s breakdown; 70% Bryce / 30% Goldman) | All | All | SIFT | Various | — | — | $69,747 |
| IV&V biannual reviews × 5 | 1.5.0; 2.5.0; 3.5.0 | All | IPAI/Purdue | IV&V partner site | ~4 each | ~$2,000 | ~$40,000 |
| Cross-team lab visit | 2.4.2 | Phase II | IPAI/Purdue | Partner lab | ~3 | ~$2,000 | ~$6,000 |
| Phase III connect-a-thon | 3.3.3 | Phase III (Month 54–57) | IPAI/Purdue + SIFT | ARPA-H site | ~10 | ~$3,000 | ~$50,000 |
| Conference dissemination | 3.5.0 | Phase II–III | Cytognosis / IPAI | TBD | ~3/yr × 3 yr | ~$2,500 | ~$22,500 |
| Travel reserve (~5%) | All | All | — | — | — | — | ~$45,000 |
| Total |  |  |  |  |  |  | ~$900,000 |

## Section 4: Other Direct Costs (ODCs) (~$6.9M)

Total ODCs over five years are approximately $6.9M. ODCs are dominated by the shared program compute line and sequencing-as-service costs.

### ODC Line Items

| ODC item | Organization | Phases | Annual est. | 5-yr total (est.) | Contribution to project |
| --- | --- | --- | --- | --- | --- |
| Shared program compute (GPU/cloud; TA1+TA2; program-level line) | Program / Cytognosis | All | ~$500,000/yr | ~$2,500,000 | TA1 causal generative model training; iterative model updates; TA2 hypothesis tournament and inference; partially shiftable to IPAI HPC in-kind |
| TA4 sequencing-as-service (scRNA-seq + Perturb-seq; CRO subaward) | Sequencing CRO | All | ~$400,000/yr | ~$2,000,000 | Phase I–III single-cell RNA-seq library sequencing for TA4 experimental data returns |
| Cloud data storage (multi-TB genomic datasets: BCA, PsychENCODE, IGoR-generated data) | Cytognosis | All | ~$100,000/yr | ~$500,000 | Long-term storage of TA1 training data, TA4 data returns, model artifacts |
| Software and API licenses | Multiple | All | ~$80,000/yr | ~$400,000 | ELN, Biorender, GitHub Enterprise, data analysis tools |
| PhD student tuition (Purdue; ~$35,000/yr per student, 2 students) | IPAI/Purdue | All | ~$70,000/yr | ~$350,000 | Tuition and fees for two Purdue PhD students |
| PM hourly fees (Patricia Purcell; ~400 hrs/yr at ~$200/hr loaded) | Cytognosis | All | ~$80,000/yr | ~$400,000 | Cross-TA coordination, delivery tracking, ARPA-H reporting |
| IT and cybersecurity compliance | Cytognosis + IPAI/Purdue | All | ~$70,000/yr | ~$350,000 | OT government-work requirements; FedRAMP-aligned data handling |
| Publication and open-source release costs | Cytognosis | Phase II–III | ~$30,000/yr | ~$150,000 | Dissemination; FAIR data deposit; open-source repo maintenance |
| ODC reserve | Multiple | All | ~$30,000/yr | ~$150,000 | Unanticipated ODC requirements |
| Total ODC |  |  | ~$1,360,000/yr (avg) | ~$6,800,000 |  |

### Materials (~$2.4M)

Materials are a separate BOE line and are detailed here for completeness; they appear as the Materials row in the consolidated BOE table.

| Material / reagent item | Organization | Phases | Qty (approx.) | Unit cost | Total (est.) |
| --- | --- | --- | --- | --- | --- |
| iPSC line acquisition and QC (WiCell, ATCC, or academic transfer) | Purdue (Tegtmeyer) | All | 10–15 lines, 5 yr | ~$5,000–15,000/line | ~$120,000 |
| NGN2 neuron differentiation reagents / consumables | Purdue (Tegtmeyer) | All | ~80 runs | ~$3,000–5,000/run | ~$400,000 |
| CRISPRi/a guide RNA libraries | Cellanome | Phase I–III | 3–4 libraries | ~$20,000–50,000/library | ~$120,000 |
| Lentivirus production and titering | Cellanome | All | ~30 preps, 5 yr | ~$5,000–10,000/prep | ~$300,000 |
| Targeted Perturb-seq kits (10x Genomics CRISPR screen kit) | Cellanome | All | ~30 screens | ~$5,000–20,000/screen | ~$600,000 |
| Cell Painting reagents | Purdue + Cellanome | All | ~50 campaigns | ~$8,000–25,000/campaign | ~$450,000 |
| scRNA-seq consumables | Cellanome | All | ~1,000 samples | ~$300–700/sample | ~$200,000 |
| CRISPR editing reagents | Purdue + Cellanome | Phase I–II | lot | ~$40,000/yr | ~$200,000 |
| Materials reserve | Multiple | All | — | — | ~$110,000 |
| Total Materials |  |  |  |  | ~$2,500,000 (~$2.4–2.5M) |

## Section 5: Resource Sharing (~$2.3M in-kind; SEPARATE from the $42.9M ARPA-H ask)

The team proposes approximately $2.3M in Performer in-kind resource sharing. Resource sharing is not required under the IGoR OT but is evaluated under Criterion 4. The in-kind contributions are substantive and documented. In-kind items do NOT count toward the ARPA-H-funded columns; they are SEPARATE from the $42.9M request.

| Resource | Contributing partner | Type | Est. value ($) | Phases | Basis |
| --- | --- | --- | --- | --- | --- |
| IPAI/Purdue HPC compute (Anvil/Brown; NSF ACCESS allocation rates) | Purdue / IPAI | HPC compute | ~$2,000,000 | All | NSF ACCESS allocation rates; a Purdue match letter unlocks ~10%; partially nets the shared-compute direct line |
| Purdue wet-lab facilities (Tegtmeyer arm) | Purdue University | Facility credit | ~$150,000 | All | Facility usage credit; covered by Purdue institutional cost-share |
| Cellanome instrument/run credits | Cellanome | Instrument/run credits | ~$160,000 | All | Needs commitment letter; clear with Duane under NDA; keep separate from Cellanome sub so no fee stacks |
| Total in-kind |  |  | ~$2,310,000 |  |  |

Do NOT count: Anne’s non-dedicated effort or Cytognosis background IP as in-kind share (ARPA-H Program Officers rate these as contestable).

Government / Performer split: - Government share (ARPA-H request): ~$42,900,000 (~94.9%) - Performer in-kind share: ~$2,300,000 (~5.1%) - Total project value: ~$45,200,000 (100%)

All in-kind contributions will be documented with letters of commitment or data-access agreements from contributing partners, attached as Appendix C.5 at submission.

## Indirect / F&A / Overhead

| Organization | Rate | Base | Regulatory basis | Notes |
| --- | --- | --- | --- | --- |
| Cytognosis Foundation | 15% de minimis MTDC | All direct costs except equipment, graduate tuition, and subaward amounts above the first $50,000 per sub | 2 CFR 200.414(f) | OT: ARPA-H negotiates actual rates; 15% de minimis is the defensible floor. A NICRA application will be submitted to DHHS within 18–24 months of award start. |
| Purdue / IPAI | ~57% on-campus MTDC | Purdue-direct salaries and ODC; excludes Purdue-issued subaward amounts above first $50,000 per 2 CFR 200.331 | Purdue negotiated F&A rate (NICRA) | Standard Big-10 research university rate; confirmed in range 55–60%. |
| McLean / HMS | ~50% on-campus MTDC | McLean/HMS sub-award direct costs | HMS negotiated rate | Applies to Ruzicka (McLean) sub only; no Broad Institute sub-award. |
| SIFT, Cellanome | Overhead embedded in fully-loaded commercial rate; F&A per Dan’s breakdown (SIFT indirect = $2,199,941) | N/A (commercial; G&A in rate) | Commercial standard | No separate F&A line for SIFT/Cellanome. Fee/profit: SIFT $636,412; Cellanome ~$600K. |

**[FLAG Duane Valz + Purdue SPS: confirm commercial-sub salary-cap treatment for SIFT/Cellanome before OT negotiation.]*

5-year indirect totals (planning estimate): - Purdue/IPAI ~57% on-campus: ~$2.36M (computational) + ~$1.3M (Tegtmeyer lab) = ~$3.7M - Cytognosis 15% de minimis on ~$8.3M MTDC base: ~$1.24M - SIFT indirect (per Dan’s breakdown): $2,199,941 - McLean/HMS ~50%: ~$0.25M - Total indirect: ~$7.4M (planning) ✓

## Note on Appendix C.4 Workbook

The Appendix C.4 Price Proposal Workbook (Excel format) is the structured companion to this narrative. It contains: Summary, By Performer x Phase, Labor, Equipment, Travel, ODC, Materials, Indirect and Fee, and Resource Sharing sheets. The workbook reflects the allocations and BOE figures in this document. Any arithmetic discrepancy between this narrative and the C.4 workbook is resolved in favor of the C.4 workbook. Workbook updated 2026-06-21 to the locked ~$43M model.

Program Manager: Patricia Purcell (Cytognosis hire), not Paul E. Sheehan, Ph.D. (ARPA-H PM). Paul E. Sheehan, Ph.D. is the ARPA-H Program Manager; Patricia Purcell is the PsychIGoR Program Manager / Delivery Lead.